## Strategic Goals
Goal ID and Development Template - Rollover (2021-22)
Strategic Direction Goals
Strategic Goals | How | Lead team | When/Period | What does success look like? | Progress
1. Safeguard the recovery of the organisation (& the sport's structures) to enable it to continue to administer the sport and support participants, stakeholders, members, clubs and talented players to recover from COVID-19 | a) Deliver a funding round/campaign to support clubs to re-engage participants back to the sport | Development & talent | Ongoing | 75% of 'normal' activity has resumed across leagues, clubs, Squads and Table Tennis England membership (normal= pre-pandemic) | From the 17th May, table tennis can resume a level of play which it has not been seen since before Christmas. Where capacity restrictions allow, clubs and other playing spaces will be able to return with no limit on group numbers. And, local leagues, local competitions and 1* events that include adults will be able to restart. As restrictions ease, we continue to prepare and publish various support documentation for players and providers to ensure effective return to play, including the launch of a 'Return to the Table' campaign to generate confidence, motivation and excitement to return as a player, coach, volunteer or official. We are currently sitting at 55% of total paid memberships and 62% of all memberships against this time last year.
| b) Support clubs and leagues to engage new participants through the suite of TTE programmes (TT Kidz, TT Fast Format, Back to TT etc) | Participation | Key time periods: September 21 & January 22 | Delivery of TT Kidz programmes in October and February, engaging a minimum of 60 clubs and 500 new participants Clubs/leagues are aware, know how to access and are delivering other programmes, such as Bat and Chat and TT Fast Format to re-engage existing and engage new participants | Preparations are underway and EOIs are now open for the September 2021 TT Kidz club programme. Coming out of lockdown we are utilising our adult participation programmes (Bat and Chat, Ping in the Community and Back to TT), to support clubs in re-engaging participants. Two new aspects of the TT Kidz programme have been launched (TT Kidz Awards Scheme and TT Kidz for Schools), and the development of a new local competitive format, TT Fast Format, has also begun.
| c) Delivery of a national volunteer recruitment campaign | Development | September 21 | TBC, x number of orgs engaged, x number of vols come forward - scope currently being outlined for the campiagn, measures to be added once recruitment campiagn has been fully mapped out. | A volunteer recruitment campaign will be launched alongside a national 'Return to the Table' campaign, to encourage people to support the return of the sport, whether as a volunteer, coach or official.
| d) Provide additional support to Talented players in the England pathway. | Performance | Ongoing | Reduced cost for players in the squads (compared with the actual cost). Increased funding to players of lower SE groups so that finance does not stop them becoming a squad member | Squads from 21/22 season (Sept 21 onwards) will be reduced as much as possible to enable it to be more accessible. 10 backing the best awards have been secured.
2. Support the well-being of staff and volunteers by providing expanded team engagements, personal development opportunities, employee assistance, and an on-going voice in direction and strategy development | a) Consult and engage staff with the SE bid for 2022 onwards | SLT | a) May - September b) to e) - Ongoing f) & g) - By July 21 | a) Staff retention | Number of working staff is 39, with 1 member of staff on furlough and 1 member of staff on reduced hours. There are 3 open vacancies, and recruitment has been paused for 1 other position.
| b) Build 'team building' time within and across teams |  |  | b) to f) staff survey responses (improvements), Improved engagement in social opportunities, plan in place for ongoing development of staff and implementation of actions following staff survey | Results from a recent staff survey are currently being analysed, to better understand employee experience and views on how we work going forward.
c) Continue to utilise online social opportunities
| d) Utilise CPD opportunities for staff & volunteers |  |  | g) Volunteer post in place and has started to develop an improved database of volunteer to provide better mechanisms of support, volunteers feel better supported (volunteer responses in membership survey) | We have hosted over 65 different webinars for volunteers, officials and coaches over the last 12 months, to maintain engagement and provide social engagement and connection to like-minded people. Regular webinars continue to be hosted for coaches and volunteers to engage and support their clubs/leagues journey back to the table.
e) work/life balance support/training
f) staff survey and follow up actions
| g) create new volunteer post to support volunteers |  |  |  | We are now out to advert for a post that will support the volunteer work of the organisation, with 1st interviews now held.
3. Refine governance processes and structures to maximise effectiveness and ensure Table Tennis England remains a high performing governed organisation/sport and compliant with the Code of Governance | a) Review articles | JKB and SS | AGM - Apr-Jul Phase 2 Q3 - Legal review | a) Neccesary improvements to the articles are accepted, supporting improved transparency and misinterpretation of the articles
| b) Complete actions from external board evaluation | JKB and SS | By September 21 | b) Cohesive board, recommendations actioned
| c) Review and update all committees ToR | JKB | By September 21 | c) More comprehensive ToR, with greater clarity of committees, terms of office and diversity | Terms of References have been reviewed to improve understanding by committees of their roles and responsibilities, including adding tenures to aid the inclusion of diversity and inclusion.
| d) Updating policies and procedures for board recruitment and induction | JKB | 2021-06-01 | d) Improved members perception of engagement/transparency of decision making and activity (membership survey/feedback). Achieveing a well balanced board of Directors in terms of diversity, skills and experiences. Directors better understanding roles and responsibilities
| e) Diversity and inclusion plan is relaunched | SLT | 2021-09-01 | e) Diversity, Equality and Inclusion action plan launched in September 21, with consultation completed, and buy in from staff, volunteers and key partners. | Significant steps have been taken towards the review and relaunch of the Diversity Action Plan. Focus groups for W&Gs, ethnically diverse communities, disability groups and LSEG communities have been established, and discussions have been facilitated by designated lead persons to capture lived experiences and views about D&I in table tennis. Further learnings from the Membership Satisfaction Survey 2021 will be used to help reshape the Diversity Action Plan, which is due to launch in September 2021
4. Continue to improve customer experience and participation levels through innovation and development of products and programmes (and relationships) | a) Continue to grow, develop and raise the profile of existing TTE programmes and TTE brand (TT Kidz, Back to TT, PPP etc) | Comps&Events/GY/Marcomms/CE | Ongoing | a) An increase in the number of clubs and organisations (and therefore participants) adopting the delivery of TTE programmes | The participation programmes have now been re-positioned on the TTE website, to allow for greater visibility and ease of access for clubs. TT Kidz sign ups for an October start are now open.
| b) Launch the TT Fast Format local league product | Participation | June 2021 launch | b) Leagues and members that are bought into the need for change following the launch of TT Fast Format, which will be achieved through X leagues signing up in the first year, creating opportunities for a more diverse range of players to be engaged and robust monitoring in place c) Use participation programmes to connect with partners and clubs to deliver table tennis to demographics that are under-represented in table tennis, piloting new ideas, generating learning and case studies to inform future activity d), e), f), g), h, i) Joined-up processes; More consistent and visible window for fixtures and results; Increased ease and time-saving for entrants, organisers and TTE staff; Ranking system meets project goals and reflects membership priorities; Regular live streaming of national events and BL Premier division; Competition programme meets project goals and reflects membership priorities; MoUs established: inconsistencies addressed and value added to all parties | Over the coming months, we will be working with select leagues to survey their members about playing preferences. The insight gained from this work will help guide the creation of a fast-format league system.
| c) Work with partners to pilot new ways of engaging with new participants we do not traditionally reach | Development | Ongoing |  | A fourth phase of targeted work with Ping! partners, where home table tennis kits were distributed to key target groups, has been completed. Evaluation of this is in progress.
| d) Launch revised ranking system | Comps&Events | For Season 22/23 |  | A review of the national rankings system has been launched, to ensure this is fit for purpose moving forward.
| e) Launch of online tournament sanctioning and entry | Comps&Events | For Season 21/22 |  | Functionality has been developed in the 'TT Memberships' platform to encompass online tournament sanctioning for organisers and online tournament entry for participants.
| f) Prepare for future online league entry, and endorsed tournament management platform | Comps&Events | During season 21/22 |  | Functionality is being developed in the Table Tennis England owned 'TT Leagues' results/ fixtures system to permit the transition of national league programmes to this platform.
| g) Prepare for launch of production and streaming platform for national competitions | Comps&Events | During season 21/22
| h) Complete competition review to better meet the needs of our participants | Comps&Events | Summer '22 for subsequent implementation
| i) MOU with partner organisations (BUCS/VETTS) etc | Comps&Events | For Season 22/23
5. Develop into a digitally driven organisation to create new revenue streams, increase efficiencies and provide better experiences | a) Development and delivery of new website to provide better customer experiences | Marcomms | 2021-09-01 | a) Delivery of new website and increase in visitations to site, decreased bounce rate and longer time on site (time spent on pages) | Since the last Board meeting all the wireframes have now been signed off, as has the homepage flat design. Remaining site design, CMS set up and web integrations are in progress.
| b) Deliver a new selection of dashboards, which include customer profiling |  | 2021-06-01 | b) Delivery before membership season 21/22 | Winners have started work on dashboards using data from Ticket Factory and Google Analytics. First drafts of the main dashboards have been delayed due to capacity problems at Sport:80. Winners are confident that they can still deliver on time (end of June – when contract with Two Circles ends).
| c) Better utilise systems (existing/new) to assist us better understand our customer data, to better target and segment our audiences. |  | Ongoing | c) ongoing digital reporting, monthly and quartely (included in Board report) | This is being done.
| d) Increase engagement on digital platforms whilst keeping up to speed on new platforms release |  | Ongoing | d) ongoing digital reporting, monthly and quartely (included in Board report) | Digital monitoring is carried out monthly which informs decisions going forward.
| e) Continue to review streaming/broadcast options to ensure we are able to maximise our reach and exposure |  | Ongoing | e) Launch of Recast and delivery of Broadcast option for 2022 Nationals | We have launched Recast (still in Beta stage), and we are currently working on a content plan. We are considering broadcasting/live streaming options.
| f) Licence IT platforms and TTE programmes (owned) to other users/nations to increase revenue | Marcomms/Ops/Participation | Ongoing | f) Exposure across other nations with opportunity for increase revenue streams
6. Commitment to improve inclusion, diversity and tackle inequalities across the organisation, governance, grassroots sport and talent pathways | a) Re-launch of the D, E & I action plan | SLT | September 21 | a) Diversity, Equality and Inclusion action plan launched in September 21, with consultation completed, and buy in from staff, volunteers and key partners. | Focus groups have been conducted with key target groups as part of the Diversity Action Plan review. Additional questions were added to the annual Membership Satisfaction Survey for key target groups. It will remain a focus to gather further insight from.
| b) Create a new role focused on D, E & I and volunteering | SLT | June 21 | b) New role in place, helping to improve the diversity of the staffing team | We have been out to recruit with over 50 applications and 1st interviews have now been held.
| c) Improve our understanding of the people in our sport and ensure we continue to collect data that enables us to understand impact | Insight | Ongoing | c) Work with Winners to build dashboards that can help us more regularly understand the diversity of our members | Winners have started work on dashboards using data from Ticket Factory and Google Analytics. First drafts of the main dashboards have been delayed due to capacity problems at Sport:80. Winners are confident that they can still deliver on time (end of June – when contract with Two Circles ends).
| d) Use insight to better understand the lived experiences of people in our sport, with a focus on W&G, disability, ethnically diverse communities and LSEG | Insight | Ongoing | d) A mechanism in place to gather insight of lived experiences in the sports from different communities on a regulatr basis | Focus groups have been conducted with key target groups as part of the Diversity Action Plan review. Additional questions were added to the annual Membership Satisfaction Survey for key target groups. It will remain a focus to gather further insight from key target groups in future research.
7. Refresh Table Tennis England 5-year strategy (Mission 2025), to reflect learnings, progress, COVID-19 impact and align with Sport England Strategy | a) Review M2025 (Board strategy day June 21) in conjunction with Sport England strategy- identifying areas of alignment | Board | 2021-06-01 | a) Membership engagement with process and development of
| b) Consultation with National Council/MAG/Membership |  | Jun - Dec | b) Published new strategy
| c) Publication of updated strategy |  | Jun - Dec | c) Investment at 'necessary level' from Sport England
SPORT ENGLAND STRATEGY
Recover and reinvent
Recovering from the biggest shock to the status quo in a lifetime, Covid-19, and reinventing as a vibrant and sustainable network of organisations providing sport and physical activity opportunities that meet the needs of different people.
An active life for a healthy life
Strengthening the connection between sport and physical activity and health and wellbeing, to enable more people to live an active life so they can live and age well.
Positive experiences for children and young people
Unrelenting focus on positive experiences as the foundations for an active life.
Strengthening communities
Focusing on sport and physical activity’s ability to create greater community development and social integration.
Active environments
Creating the places and spaces that make it easier for people to be active.