## 2022
Implementation Plan: | BPTT & TTE Partnership and Shared Goals |  | Current Picture
Date Created: | 2022-01-19
Date last updated: | 2022-05-24
Members: | Aled Howell-AH Greg Yarnall - GY Karen Tonge - KT Matt Stanforth - MS Zoiey Smale - ZS
Communication Plan: | 6 weeks Teams
Last date of last meeting: | 2022-05-24
Objectives/Aims | Baseline/ Initial Picture | Original actions | Timescale for Completion | 2022-10-25 | 2022-08-15 | Current update 24/05 | Update - 13/04 | Previous update/notes
Supporting Para player training | There is an opportunity for joint Performance camps at EIS sheff SM has identified the following dates: - 8-12th August - 15-19th August - 22nd/23rd October | MS to confirm if any of the dates suit | 31st July 2022 | Pathway planning 13th December (Both - BPTT & TTE) - Sheffield MS to attend. |  |  | Matt to review BPTT & TTE implementation plan | 13/04/22 MS was unable to attend. GY has asked MS to review this document.
|  | SM to pick up actions with MS on how performance camps could work | 31st July 2022 | SM & MS to dicuss dates for the performance camps - December 2022 |  | Pathway under review | Matt to confirm if these dates suit? | 2 sessions per day, rough times 9am-11.30am, 2.30pm-5pm. We do have the hall available from 9am to 5pm - SM
|  | KT to be involved across the camps. | 31st July 2022 | SM changed match play days changed from training days. (22nd + 23rd) Future development with more Match Play days. |  |  | Shaun look at opportunites with EIS Practitioner led workshops. | Across the 2 weeks we are looking at planning three workshops; Media Training with Francesca Bullock, Rules with KT and UK Anti-Doping, dates TBC.
|  | SM looking at opportunity with . Could MS bring players to EIS Sheff? |  | N/A | Matt to confirm if weekend suits and whether will invite players | Matt to find a suitable date. Weekday is a preference | Matt, if there are any days that you would like to bring some players let Shaun know | We have 10-12 tables per day, we will open it to 'first come, first served' and cap it with a max. of 14.
| How can we ensure Para players are embedded within England squads? | MS to update | March 2022 - meeting |  |  | Shaun to send Matt dates so that two diaries to scope for future opportunities. Matt has ringfenced budget to help support this objective.
| Explore opportunity for England coaches to have training on eligible impairments so they are able to identify players that may be eligible for the Para pathway at an earlier age | SM to offer a half day session for all coaches to look at: • Eligible v non eligible impairments •Classification - Class 1 to 11 •How to work with Wheelchair athletes |  | One player put forward with the coaching team. MS to send dates to SM. | SM and MS to progress/find dates | TTE GB apprentice coaches to work on Talent eligability days / be provided with opportunities to support - Shaun to meet with Simon | Matt to check dates and connect with Shaun | SM proposes the following: Oct workshop eligible v non eligible impairments, Nov workshop Classifcation - class 1 to 11, Dec - how to work with wheelchair athletes. Happy to explore either online via zoom or in person workshops. SM
Educate the coaching and volunteer workforce to support them to feel more confident and capable of coaching Disability table tennis | Explore what a series of Para coaching clinics could look like: •W/C 13th June - Working with wheelchair athletes •W/C 17th October - Classification | SM and Neil Robinson to pick 2 evenings for delivery |  | SM to send dates for this to be lauched. W/C 13th Feburary? | AH to update and speak with Shaun - potential for w/c 10th Oct - AH to confirm with Shaun and arrange details | Aled to promote op in UK coaching week Shaun to confirm for 5th Sept | Shaun to let us know a new June date due to clashes with CLS event. | 14th June evening, SM & NR deliver a workshop on working with wheelchair athletes (confirmed). 18th Oct, SM & Rachel Hutchinson (BPTT Classifier) to deliver a workshop on Classification (TBC)
|  | AH and SM to discuss how to move thing forward |  | Wheel power coaching course - £8000. Trainig courses to link in with the wheel power training. Linked in with the 8 Spinal Injury unit courses. | AH to provide update | No further action needed. Project will be open for clubs to apply | SM +AH to arrange a catch up to discuss Wheelpower project proposal | Aled do the above dates look ok? Shall we look at building a plan for the next few years for other topics - SM - dates look fine but we have some potetnial links with Wheel Power that could tie in nicely.
|  | AH to share information on event to Relevant TTE stakeholders |  |  |  | Update for next meeting
|  | AH to move precorded coaching clinics to on demand TTE platform |  | SM & NR to work on online material 'How to coach' |  | AH + SM to pick up conversations on how the 2x webinars will work. |  | Shauns previous webinar can be found on our Coaching Support page within TT Learning Zone
Wheel power project | Aled is leading on the Wheelpower project. |  |  |  |  | Update in next meeting |  | Upskilling of coaches, AH and CLS meeting with Emily to get clubs to apply
Increase the number of Disabled coaches | Run a level 1 course across Para squads that links in with BPTT's performance exit strategy. Implement an on going process where Level 1 and Level 2 coaching qualification run on alternating years. | AH to build this into Coaching and Officiating strategy |  | Wednesday 14th December, 1st Feburary - Dates for the … | SM to feed into individual athlete plans and exit strategies taking place after the Worlds in November. |  | update needed
|  | SM to potentially register for cohort of tutors in 2023? | 31st December 2022 | Tutor course 25th - 26th of Feb in Milton Keynes. | How do we plan in any Level 1 training for early 2023 that doesn’t clash with prep for qualifying yeare for Paris 2024 |  |  | SM to look to do tutor course in 2023
|  | AH, and SM to meet to discuss how the course could run that is most cost effective. Send plans to Greg | 24th March 2022 |  |  |  |  | Courses – these would need to be arrange and plan pulled together via a meeting between Aled and Shaun Marples
|  | GY to review/confirm TTE spend from TTE diversity pot | 31st March 2022 | AH & DR to investigate with Bekki |  |  | Update needed
| Promote the Charlie Childs funding across BPTT membership to support up to 50% of L1 course costs | ZS to send the link to SM | 19th Jan 2022 | Case study from Pedro, AH to release |  |  |  | Charlie childs grant is being used in conjuntion to support TTE coach.
|  | SM to promote the opportunity to interested parties | 19th Jan 2022 | Continuation on Promotion, Looking to add funding to the pot per year. |  |  |  | Complete, BPTT to host a Level 1 Umpires course on Saturday 22nd Oct - SM
| TTE to collect and promote case studies of current coaches | AH to provide ZS with contacts and emails | 19th Jan 2022 |  |  |  |  | • Harry Fairchild •Ryan Morton •Craig Allen • Dan Bullen • Shaun Newcomb •Neil Robinson •Steve Brunskill
|  | ZS to identify if there are any awareness days in the inclusion cal which would be good to help raise profiles. Share at next meeting. | March 2022 - Meeting |  | Opportunity for blogs similar to Jan Fuller (Parkinsons) - SM and Fran to identify couple of players |  |  | 1st March - International wheelchair day March IWD April - Loss of Limb awareness Month | Disability Awareness Days 2022 ¦ EFDNI
|  | ZS to collect content to share about Simon Heaps | End of April |  | SM to confirm if can use case studies as part of UK Sport strategy work |  | ZS to speak to Marcomms and Paul about featuring Simon Heaps story | Paul will make contact with Simon. H after easter.
|  | SM to share info/videos RE case study player journey |  |  | BPTT better understanding stories of athletes and whether there are any case studies/inspirational stories to pull out and use. |  | double-amputee-heaps-still-pushing-on-the-international-stage | Shaun to send ZS details
|  | AH to share round casestudy template | 1st March 2022 |  |  |  |  | Shared via email | Coach_Story Collection Template.docx
| Record and upload content to TT learning Zone | Everyone to send useful recordings/content to AH so that relevent information can be added to TT Learning Zone | Ongoing | Coaching facebook page, sharing different coaching content. BPTT Coaching encouraged to join. |  |  |  | Nothing to upload at the moment, SM currently updating the Pathway Prospectus
Increase opportunity for Disabled people through Universities | BPTT now working more closely with University of Sheffield and Sheffield Hallam University to support players that have moved to Sheffield to complete a degree, alongside train at EIS. Pilot for universities and W&G's work is parked for now as awaiting results of a feasibility study. | Awaiting results of feasibility study | TBC | Gregs Lead | Will now start in September with completion by December 23 | MLS commissioned to do the work. Greg to update in next meeting.
| Exploring opportuities with BUCS. Disability/para competitions added to a BUCS event? BUCS to introduce a Para-section? | SM to link GY with Jordan as a contact |  | DB to discuss with SM with info if and when. | BUCS should be in contact with SM to discuss which categories would work etc for inclusion in 22 or 23 champs |  | Shaun to send Jordan and Simon Vardy's email addresses to Greg | 3 players (Shae Thakker, Joe Crouse, Ryan Henry) will be going to the European University Championships for Para Table Tennis in July.
|  | GY to feedback discussion points to BUCS group |  | Pathway to remain active through the universities. Patnerships to remain with UNI'S both TTE & BPTT. New works with Birmingham Uni (Coaching partnership) |  | GY to share BUCS meeting invite to Shaun Update needed in next meeting | Greg to update once meeting has been had | BUCS indiv championships. Main BUCS lead is stepping away, looking for a new chair. Still waiting on a follow on meeting. 13/04/22
| Make universities aware of the Level the table grant | SM shared with Jordan Butler SHU and Simon Vardy Uni of Sheff. Seeking an email to send to Sarah McQueen also Uni of Sheff | 19th Jan 2022 |  |  |  |  | Complete. Zoiey do you have an update on Tees university? Happy to link a club visit around doing something with them SM | ZS in contact with tees university
| TTE to work with Tees university to help them set up a Para TT section. ZS is in contact with TH at TUSU. Equipment of 8-10 tables and bats and balls. Just need a coach | Plan a project proposal | 16th Feb 2022 |  |  | New TTE projects officer to pick up this conversation with Tees | ZS to link Shaun and Greg with Tom at Tees university | developments are on hold for now as department is having a reshuffle (tees). Tees could be a good place for talent eligability days.
|  | Find a coach to deliver | ongoing |  |  |  | TBC when Project plan has been discussed after June. | https://www.tabletennisengland.co.uk/advertise-your-positions/
· Eligibility/Talent Recruitment days | BPTT pre-pandemic held a successful day in St Neots. Keen to run again and perhaps spread round the country with one in North and South. • W/C 25th April •W/C 11th July •W/C 15th August - linked with BPTT Summer camp •W/C 19th September | ZS to review how this would work, do we need a NSEW venue, TTE to support with some of the funding | Plan proposal delivery for March 2022 meeting | From Janurary, working with para athletes and next steps. Going around each club per month. SM to attend all clubs pathway days - Furture vision clubs then becoming pathway clubs. | 8 clubs come forward, following application process, to run talent recruitment taster sessions. SM suggestion we try and get round all of them. Provide clubs with what the outcomes of these days should be, e.g. for players from club to be identified and invited to Sheffield, players to come across from local area/regions, needs to be marketed out to clubs and membership. Demi to identify next steps, SM to send to Demi summary fo what we want to achieve to share with clubs | New TTE projects officer to pick up this conversation with Tees | Shaun to create Talent recruitment plan. | 25th April cancelled. Campaign to collect information to generate interest. CLS to add an article in newsletter. Registeration of interest form to be created by ZS | Check open call for venue - or support for players
|  | ZS to speak to CLS about TRD |  | 2 clubs yet to confim dates, SM to follow up with this. |  |  | ZS to email claire | ZS emailed claire. Meeting to be had to review end of April
|  | ZS to email CLS to get a feature in the CLS newsletter | 16th Feb 2022 |  |  |  |  | Talent recruitment days have been flagged to feature in CLS newsetter
Increase the number of wheelchair players on the Para pathway (class 1-5) | Grow connections with Spinal Injury Unit Centres across the country. TTE identified an opportunity with Level the Table funding that could potentially help support to expand delivery and club connections • Sheffield – Alex Jewitt • Pinderfields - • Southport - • Salisbury – Shaun Newcomb • Stoke Mandeville - • Stanmore – • James Cook SM looking at BPTT Funding for 1 hour per week coaching across following sites; • Cardiff – Rookwood • Glasgow – • Sheffield – • Pinderfields – • James Cook (Middlesborough) – Steve Brunskill | GY + ZS identify Nearest clubs to SIU – mapping exercise - | 16th Feb | Pilot project across 4 SIU. Two coaches intenified to go in the units so far. 3 of the 4 units been intouch. Start from Jan 2023 | Demi to email Emily with Shaun copied in to kickstart project and understand provision across sites. Demi and Shaun to identify coaches/clubs that can go in and support. Aim to start project in October. |  |  | Complete - In the LTT ops plan
|  | SM to create a project proposal which includes cost and how much BPTT are putting towards the projects | 15th February 2022 | SM to recruit the remaining coaches for the Unit. DR + sm to finalise coaching days with unit and equipment requirements |  | Job advert to be created ZS to draft email 24/05. Shaun to email SIU's | Shaun to contact SIU's | SM Shared project costs with TTE, any feedback before I start to contact the spinal units to arrange coaches to deliver? Feedback is supportive and TTE have ringfenced funds to support this.
| Support Wheelpower at National Junior games (June) and Spinal injury Games (Sept) showcasing our sport at the event. | ZS + SM to email potential coaches | 16th Feb | N/A |  |  |  | AR,DB,PS
Increase Competition opportunity and accessibility | BPTT are encouraging more and more competition opportunities for their players, however this can be challenging for the wheelchair players with the lack of wheelchair friendly tables. BPTT competition dates;  5/6th March – EIS Sheffield  28/29th May – EIS Sheffield  24/25th September  22/23rd October 29th/30th October - Nationals  26/27th November – St Neots | No actions were set |  | DB Organising team to run the event - St Neots. Nationals event Cancelled. |  |  |  | Date changes: Nationals now 29th/30th October
| Tender for Grand Prix table suppliers that min. of 1-2 wheelchair friendly tables are provided. | GY to pick up conversations with Neil Rogers to feedback from January meeting. Including changing tables at Senior National finals |  |  | Regs are now going to be included that competitions to include a wheelchair compliant table | Greg, Neil to speak to Shaun to review |  | Date in diary for meeting GY + NR. Wheelchair compliant tables included in tender.
| BPTT players to be included in competition |  |  | DR to pick up with Neil, disability card who havent been to a classification card and the relevant requirements for disbility players such as tables for wheel chair users, ect. | Online entries to now be introduced for all TTE competitions, which will enable individuals to identify if they have a Disability and if they are in a wheelchair Video created for education around difference in rules for wheelchair players etc - AH leading and aim for Sep 22 |  | Update in next meeting
| Ensure appropriate mechanisms are in place when wheelchair players are competiting |  |  |  | 4 Para events per year - next one in Halton - 24th/25th Sep and then 26th/27th November in St Neots
|  | GY to speak with Events on having a section asking if a player uses a wheelchair |  |  | Increased entry from BPTT players into British League, mainly through Brighton TTC
| Para categories to be included across an increasing number of National age group champiionships | NR to work with SM to identify the age groups/categories where this may be possible |  |  | Para categories to be included in Cadet and Junior Nationals for 22-23 season if appetite/number of entries/critical mass is there
| Para players to have cards that identify their Disability and any adaptations required for service | JMH to design this |  |  | Reminder that players to take classification cards to competitions - Include on online entry form?? - Demi to follow up with Neil | Shaun to share |  | No update at the moment - SM
Sharing membership data | Have an eligiblity impairments sheet that could be sent round to anyone identifying as having a Disability with a question also about whether they would also like to hear more from BPTT | SM to share this with TTE |  | SM released a list of impairements asking to get intouch if eligble. Still work to be done. | SM has shared some wording with NR to send some comms to TTE members that have identfied they have a disability. NR passed on to Jo Keay Blyth | Shaun to share |  | No update at the moment - SM
Raise awareness of Para players and their journey | Share case study/stories/interviews and promote across our membership. This could be linked to awareness days | Profiles to go live on BPTT first. Pick up in next meeting |  | Still with BPTT - Review | As case study section |  |  | Case studies; Felicity Pickard Lee York Jacob Pritchard Webb Shae Thakker Theo Bishop
B2022 Legacy funding from Sport England | B2022 funding | Greg to update the group |  | DR to pick this up with SM & CE. |  | ZS/GY to pick up with CLS |  | Talent ID to link in to B2022 funding. St Neots, Swerve TT, Halton TT through Karen. CLS has been contacted about expression of interest.

## SIU Project
SIU's |  |  |  | Timeline | [5 empty] | Resources
Project | Location | Contact | Status | Planned Start | Actual Start | Planned Finish | Actual Finish | Ahead/Behind | Number of Participants | BPTT | TTE | Equipment | Notes
1. Create strong links with clubs around the Spinal Injury Units, which could lead to increasing TTE membership. 2. BPTT developed links to signpost the potential performance athletes through to Sheffield, into the Futures programme. 4-6 participants across each site each week. That would be somewhere between 28-42 participants. The demographic of the particpants, would generally be older, around 50+ years of age. But there will be the will be that participant every so often, which will suit the profile for the Para Table Tennis pathway. | Sheffield | Alex Jewitt |  | 1st April 2022 | [5 empty] | 1040 | 200 |  | 1 x £20 per week x 52 weeks = £1040 starting March 2022
| Pinderfields | under recruitment |  | 1st April 2022 | [5 empty] | 1040 |  |  | 1 x £20 per week x 52 weeks = £1040
| Southport | Helen Gilian |  | 1st April 2022 | [5 empty] | 1040 | 800 | Bats, Balls & Nets | 1 x £20 per week x 52 weeks = £1040 + £800 for equipment
| Sailsbury | Shaun Newcomb |  | 1st April 2022 | [5 empty] | 600 | 1240 | Bats,Balls, Ball Pickers, Bat Covers, Bat Cleaner | 1 x £20 per week x 52 weeks = £1040 + £800 for equipment
| Stoke Mandeville | Ian Durrant/Bob O'Shea |  | 1st April 2022 | [5 empty] | 1040 | 800 | Bats & Balls, 1 Table | 1 x £20 per week x 52 weeks = £1040 + £800 for equipment
| Stanmore | Mark O'Neill |  | 1st April 2022 | [6 empty] | 1040
| Middlesborough | Clair Williams |  | 1st April 2022 | [5 empty] | 1040 |  |  | 1 x £20 per week x 52 weeks = £1040

## SIU and Club Link
Spinal Injury Unit | Closest clubs | Type | Miles | CSO
Sheffield S5 7AU | Northern General SC | Associate | 0.05
| Shiregreen TTC | Associate | 0.53
| Vulcan (Redtooth) TTC | Premier | 1.44 | Martin
| Wadsley Bridge TTC | Premier. | 2.89 | Andrea
| Abbeydale Park Table Tennis Club | Premier | 6.43 | Andrea
Pinderfields WF1 4DG | Ackworth Table Tennis Club | Premier. | 7.91 | Martin
| Barnsley Table Tennis Club | Associate | 9.76
| Pudsey TTC | Premier. | 10.26 | Johnathon
| Leeds Judean TTC | Associate | 10.8
| Deighton Table Tennis Premier Ability Club | Premier | 12.15 | Andrea
Southport PR8 6PN | Southport Table Tennis Club | Associate | 1.28
| Prebond Table Tennis Club | Associate | 7.25
| Bath Street Marine Table Tennis Club | Premier | 10.47 | Andrea
| Blackpool TTC | Premier | 12.56 | Martin
| Preston Table Tennis Club | Premier | 14.44 | Martin
Sailsbury SP2 8BJ | Chalke Valley Table Tennis Club | Associate | 6.37
| Waterside TTC | Premier | 15.31 | Andrea
| Southampton West Table Tennis Club | Associate | 16.83
Stoke Mandeville HP21 8A | Chiltern Table Tennis Club | Associate | 8.04
| St Christopher Table Tennis Club | Associate | 9.74
| Chesham Grammar School (CGS) TTC | Associate | 10.61
| Dacorum Table Tennis Club | Associate | 13.93
| Oxford Community TTC | Premier | 18.13 | Martin
Middlesborough TS4 3BW | Swerve Table Tennis Club | Premier | 0.27 | Martin
| Ormesby TTC | Premier | 1.13 | Andrea
| Northfield TTC | Premier | 5.93 | Johnathon
| Hartlepool Table Tennis Academy | Associate | 11
| Darlington Dolphins Table Tennis Club | Premier | 13.74 | Andrea
Stanmore HA7 4AP | London Table Tennis Academy | Premier | 1.05 | Johnathon
| Stanmore Table tennis Club | Associate | 1.25
| Elstree and Borehamwood Table Tennis | Premier | 2.69 | Andrea
| Watford Table Tennis Club | Premier | 4.49 | Martin
| Urban Table Tennis Club | Premier | 5.14 | Andrea

## Past AOB
Strengthen DiSE programme (NEW) | Chris Turner was in the Performance Team running the DiSE programme (Diploma in Sporting Excellence) which is aimed at 16 -18 year olds who are in 6th Form / College aiming to balance a performance journey along with academic studies. They undertake modules related to performance sport applied to their own setting (strength & conditioning, psychology, nutrition etc) and is worth 64 UCAS points upon completion. There are four athletes (out of 12) who are part of that programme now in their second year of the course who are on the BPTT pathway. | Identify players in that age group within BPTT remit
Fast format (NEW) | Could we look to possibly work along with the EIS to look to set up a Fast Format League if funding can be sort as Colin mentioned from the Commonwealth Games. Sheffield League is struggling and a central venue for fast format like the EIS would be super for Juniors, adults, Disability players, community players etc everyone to have an opportunity to join and play? | Discuss
Regional inclusion workshops facts figures and resources - Plain text.docx